Immunodeficiency Gene Reference Sequence Pipeline

Pipeline Documentation & Progress Record

As of March 2026  |  Lund University Thesis Project

| DONE | DONE | DONE | DONE | IN PROGRESS | PLANNED |
| --- | --- | --- | --- | --- | --- |
| 1. IDbases Summary | 2. RSG Scraping | 3. Seq Download | 4. BLAST Submit | 5. BED File Creation | 6. Mutalyzer Analysis |

# 1. Project Overview

This pipeline establishes reference sequences for 131 immunodeficiency genes catalogued in the IDbases project (Lund University), enabling standardised mutation reporting via Mutalyzer. The pipeline maps IDbases gene entries to NCBI RefSeqGene (RSG) records and human genome assemblies (hg16/17/18) to produce BED files and Mutalyzer-compatible variant descriptions.

Thesis context: The ADA RefSeqGene (NG_007385.1, LRG_16) was used as the prototype. It is a full genomic sequence (~32 kb) covering the entire gene locus including all exons, introns, and flanking regions — not just the CDS. All other RSG records follow the same convention.

## 1.1 Key Resources

- IDbases portal: structure.bmc.lu.se/idbase — 131 immunodeficiency mutation databases

- LRG_RefSeqGene mapping: LRG_RefSeqGene.txt (downloaded from NCBI FTP)

- LUNARC (Cosmos): HPC cluster at Lund University used for BLAST jobs

- Mutalyzer: https://mutalyzer.nl — variant description normalisation and liftover

## 1.2 Gene Coverage

- Total IDbases genes: 131

- Genes with RSG in LRG_RefSeqGene.txt: subset (scraped → LRG.csv)

- Genes without RSG: missing from LRG_RefSeqGene.txt — noted in LRG.csv, no RSG assigned

- All available sequences downloaded: Yes (mRNA EMBL flat-files via ENA + FASTA)

# 2. Pipeline Steps

Step 1  IDbases Summary & UniProt Mapping   [DONE]

| Input | IDbases pub.html files (one per gene in /idbase/) |
| --- | --- |
| Output | IDBases_Summary_with_UniProt.xlsx — gene list with columns: name, UniProt ID, and mutation metadata |
| Script | extract_mutations.py → produces all_mutations.tsv (manual UniProt column added to produce final XLSX) |
| Notes | extract_mutations.py parses /loc: IDRefSeq entries from each *pub.html file. UniProt IDs were added from IDbases summary page data. Genes without a UniProt ID are tracked but not excluded. |

Step 2  RefSeqGene (RSG) Scraping from LRG_RefSeqGene.txt   [DONE]

| Input | LRG_RefSeqGene.txt — NCBI FTP mapping file of LRG accessions to RefSeqGene NG_ accessions |
| --- | --- |
| Output | LRG.csv — IDbases genes annotated with their NG_ accession (where available); genes absent from the file have no RSG entry |
| Script | (custom scraping / parsing script — grep/pandas against LRG_RefSeqGene.txt) |
| Notes | Some IDbases genes have no entry in LRG_RefSeqGene.txt. This is expected — not all immunodeficiency genes have a curated RSG. Missing RSGs are recorded as blank in LRG.csv and may require manual lookup or alternative reference strategies. |

Step 3  Sequence Download (EMBL mRNA + FASTA)   [DONE]

| Input | IDBases_Summary_with_UniProt.xlsx (gene + UniProt ID list) |
| --- | --- |
| Output | Per-gene sub-folders under Mutation Extraction and Matching/: <accession>.embl + <accession>.fasta files; download_summary.csv; download_log.txt |
| Script | download_embl_sequences.py process_embl_mutations.py copy_reference_sequences.py |
| Notes | UniProt REST API queried for mRNA-type EMBL cross-references. EMBL flat-files fetched from ENA. CDS offset auto-extracted from EMBL feature tables. Mutations cross-checked against sequences; full-match sequences copied to Reference sequence/ folder. All available sequences downloaded regardless of RSG availability. |

Step 4  BLAST Against hg16 / hg17 / hg18   [DONE]

| Input | FASTA sequences from Reference sequence/ folder (one per gene where a full mutation match was found) |
| --- | --- |
| Output | BLAST result files on LUNARC Aurora; blast_all.sh job script |
| Script | blast_all.sh (submitted to LUNARC SLURM queue) blatn against hg16, hg17, hg18 genome databases |
| Notes | BLAST run on LUNARC HPC using SLURM. Target databases: UCSC hg16, hg17, hg18. Output format includes alignment coordinates for BED file extraction. Job monitored via LUNARC Aurora portal. |

Step 5  Extract Top BLAST Hits & Create BED Files   [IN PROGRESS]

| Input | BLAST output files from Step 4 |
| --- | --- |
| Output | Per-gene BED files for 100% identity hits; mutation_summary BED file overlaying mutation positions on genomic coordinates |
| Script | (planned: parse_blast_hits.py or equivalent) |
| Notes | For each gene: extract the first/best BLAST hit (100% identity, full-length alignment). Convert HSP coordinates to BED format (0-based, half-open). Overlay mutation positions from all_mutations.tsv to produce a combined mutation+coordinates BED for each genome assembly. |

Step 6  Mutalyzer Variant Description & Liftover   [PLANNED]

| Input | BED files from Step 5; LRG.csv (RSG accessions); all_mutations.tsv |
| --- | --- |
| Output | Mutalyzer-normalised variant descriptions in HGVS format; liftover to current genome assembly; updated mutation database annotations |
| Script | (planned: mutalyzer_batch.py — Mutalyzer REST API or batch submission) |
| Notes | Use Mutalyzer position converter to map variants from hg16/17/18 coordinates to current assembly. For genes with RSG: generate NG_-based HGVS descriptions. For genes without RSG: use chromosomal (NC_) descriptions. Output will feed back into the IDbases mutation records. |

# 3. File & Directory Structure

Thesis root:  C:\Users\BornLoser\Desktop\Assignment\Thesis\

| Path | Description |
| --- | --- |
| idbase/ | Raw IDbases pub.html files, one sub-folder per gene (e.g. ADAbase/) |
| all_mutations.tsv | All extracted DNA mutations from all IDbases genes (Step 1 output) |
| IDBases_Summary_with_UniProt.xlsx | Gene list with UniProt IDs (Step 1 output, used by Steps 2–3) |
| LRG_RefSeqGene.txt | NCBI FTP LRG→RSG mapping file (source for Step 2) |
| LRG.csv | IDbases genes with NG_ RSG accessions where available (Step 2 output) |
| Mutation Extraction and Matching/ | Root for per-gene EMBL/FASTA/mutation work (Step 3) |
| Mutation Extraction and Matching/<gene>/ | Per-gene folder: .embl, .fasta, mutation check CSVs |
| Mutation Extraction and Matching/download_summary.csv | Summary of EMBL download results per gene |
| Mutation Extraction and Matching/process_summary.csv | Summary of mutation cross-check results; lists matched accessions |
| Reference sequence/ | Copied FASTA files for genes with full mutation match (Step 3 output, BLAST input) |
| Reference sequence/<accession>_<GENE>.fasta | e.g. X02994_ADA.fasta — reference sequence per gene |
| blast_all.sh | SLURM job script for LUNARC BLAST runs (Step 4) |
| BLAST results/ | (Step 4 output) Raw BLAST output files per gene vs hg16/17/18 |
| BED files/ | (Step 5 — planned) BED files for 100% hit coordinates + mutations |

# 4. Scripts Reference

| Script | Step | Purpose |
| --- | --- | --- |
| extract_mutations.py | 1 | Parse IDbases pub.html files → all_mutations.tsv. Extracts gene, accession, position, mutation type from /loc: IDRefSeq entries. |
| download_embl_sequences.py | 3 | Query UniProt REST API for mRNA EMBL accessions per gene. Download EMBL flat-files from ENA. Handles resume (skip existing), rate limiting, logging. |
| process_embl_mutations.py | 3 | Convert EMBL → FASTA. Auto-extract CDS offset from EMBL feature tables. Cross-check mutation positions against sequences. Identify full-match reference sequences. |
| copy_reference_sequences.py | 3 | Copy matched FASTA files to Reference sequence/ folder with <accession>_<GENE>.fasta naming. Skips genes with 0 or >3 matches. |
| blast_all.sh | 4 | SLURM batch script submitted to LUNARC Aurora. Runs blastn for each reference FASTA against hg16, hg17, hg18 genome databases. |

# 5. Immediate Next Steps

## 5.1 Retrieve BLAST Results (Step 5a)

- Collect all BLAST output files from LUNARC (scp or Aurora file browser)

- Parse: extract the top hit per gene (highest identity / longest alignment)

- Filter for 100% identity hits only — these become the genomic anchors for BED files

- Record: chromosome, start, end, strand, query length, % identity, e-value

## 5.2 Create BED Files (Step 5b)

- Convert BLAST HSP coordinates to BED format (0-based, half-open, UCSC convention)

- One BED per assembly (hg16, hg17, hg18) with gene name and accession in name field

- Second BED: overlay mutation positions (from all_mutations.tsv) onto genomic coordinates using CDS offset from process_embl_mutations.py

- Validate in UCSC Genome Browser

## 5.3 Mutalyzer Variant Normalisation (Step 6)

- For genes with RSG (LRG.csv): build HGVS descriptions relative to NG_ accession

- For genes without RSG: use chromosomal NC_ reference (hg38) via liftover from BED coordinates

- Submit to Mutalyzer position converter API in batch

- Map hg16/17/18 → hg38 (GRCh38) to get current assembly coordinates

- Output: updated HGVS variant descriptions for IDbases entries

# 6. Known Issues & Notes

- Missing RSGs: Genes absent from LRG_RefSeqGene.txt have no NG_ accession. For these, chromosomal (NC_) references should be used for Mutalyzer. Tracked in LRG.csv as blank.

- Genome versions: IDbases mutations reference hg16/17/18 coordinates depending on when they were curated. BLAST against all three ensures the correct assembly is identified per mutation.

- RefSeqGene = full genomic: NG_ accessions cover the entire gene locus (exons + introns + flanking). They are not CDS-only. This affects coordinate mapping — CDS offset must be applied when converting mutation positions.

- Mutalyzer liftover: Mutalyzer's position converter supports NC_-based variants. For NG_-based variants, use the mapping tool with the LRG transcript as intermediary.